|  |  |  |  |
| --- | --- | --- | --- |
| **Tasks** | **Start date** | **Finish date** | **Comment** |
| Project plan  Creating a video based on the organisation WWE and promoting the company in order to attract viewers (so they can watch the televised show) and customers (in order to get them to but tickets to shows and to buy merchandise). | | | |
| Research  Planning out the project | 4-10-2013  18-10-2013 | 18-10-2013  25-10-2013 | Completed, deadline met  Completed, deadline met |
| Producing project specification | 25-10-2013 | 8-11-2013 | Completed, deadline has been met |
| Producing a project plan | 15-11-2013 | 22-11-2013 | Completed |
| Implementation &Designing | 06-12-2013 | 13-12-2013 | Not yet started |
| Reviewing and creating a questionnaire  Produce a presentation | 10-01-2014  24-01-2014 | 24-01-2014  07-02-2014 | Not yet started |
| Review – Writing a report | 14-02-2014 | 21-03-2014 | Not yet started |