|  |  |  |  |
| --- | --- | --- | --- |
| **Tasks** | **Start date** | **Finish date** | **Comment** |
| Project plan Creating a video based on the organisation WWE and promoting the company in order to attract viewers (so they can watch the televised show) and customers (in order to get them to but tickets to shows and to buy merchandise). |
| ResearchPlanning out the project | 4-10-201318-10-2013 | 18-10-201325-10-2013 | Completed, deadline metCompleted, deadline met |
| Producing project specification | 25-10-2013 | 8-11-2013 | Completed, deadline has been met |
| Producing a project plan | 15-11-2013 | 22-11-2013 | Completed |
| Implementation &Designing | 06-12-2013 | 13-12-2013 | Not yet started |
| Reviewing and creating a questionnaire Produce a presentation | 10-01-201424-01-2014 | 24-01-201407-02-2014 | Not yet started |
| Review – Writing a report | 14-02-2014 | 21-03-2014 | Not yet started |